Estimate dev timeline realistically for solo founder

I’ll give you a realistic solo founder timeline, assuming:

You are strong in backend/cloud

Working ~20–25 hrs/week (side project)

No full-time designer

Using modern stack (Next.js + NestJS/FastAPI + Postgres + AWS)

Building proper multi-tenant SaaS (not hacky MVP)

🧠 Big Truth First

For this level of MVP (multi-tenant, ticket engine, vendors, storm mode, reporting):

Full-time (40h/week): 4–6 months
Part-time (20–25h/week): 6–9 months

Anything faster means cutting scope heavily.

🏗 Phase-by-Phase Timeline

Phase 0 — Validation (2–3 weeks)

Before heavy coding.

Tasks:

Interview 8–12 Jacksonville property managers

Confirm maintenance pain points

Validate storm + landscaping workflows

Identify what software they use now

Time:

10–15 hours total

Can overlap with light backend setup

If you skip this → risk building wrong thing.

Phase 1 — Foundation & Multi-Tenant Core (4–6 weeks)

This is serious backend work.

Backend:

Auth (JWT + RBAC)

Multi-tenant isolation

Management companies

Users

Communities

Vendors

Assets

File upload to S3

Basic logging

DB migrations

Frontend:

Login

Admin dashboard skeleton

CRUD for communities/vendors/assets

Estimated time:

Backend: 80–100 hours

Frontend: 40–60 hours

If you're disciplined → 1 month part-time.

Phase 2 — Maintenance Ticket Engine (6–8 weeks)

This is the core complexity.

Build:

Ticket creation

Assignment flow

Status transitions

SLA timers

Ticket history tracking

Photo uploads

Vendor portal view

Basic filtering/search

Overdue detection

Hard parts:

Clean UX flow

Status lifecycle logic

Multi-role access control

Estimated:

Backend: 100–120 hours

Frontend: 80–100 hours

This is your heaviest lift.

Phase 3 — Florida Differentiators (4–6 weeks)

This includes:

🌪 Storm Mode

Storm event table

Tagging system

Dashboard filter

Storm report export

🌴 Recurring Landscaping

Template system

Scheduled ticket generation

Checklist storage (JSONB)

Compliance photos

🏊 Pool Logs

Simple form + reporting

Estimated:

60–100 hours total

You could cut pool logs to reduce time.

Phase 4 — Reporting Engine (3–4 weeks)

This part always takes longer than expected.

Build:

Ticket metrics queries

Vendor SLA calculations

Cost summaries

PDF generation

Monthly board report template

If you try to overdesign charts → delay.

Estimated:

50–70 hours

Phase 5 — Polishing & Production Hardening (4–6 weeks)

This is what most devs forget.

Includes:

Error handling

Edge cases

Role permissions testing

Load testing

Logging & monitoring

Email notifications

Data validation

UI cleanup

Mobile responsiveness

Basic onboarding flow

Estimated:

60–100 hours

⏱ Realistic Total Effort

If we total conservative hours:

| Phase | Hours |
| --- | --- |
| Validation | 15 |
| Foundation | 150 |
| Ticket Engine | 200 |
| Florida Features | 80 |
| Reporting | 60 |
| Hardening | 80 |
| Total | 585 hours |

If you work:

20 hours/week → ~29 weeks (~7 months)

25 hours/week → ~23 weeks (~5.5 months)

40 hours/week → ~14–16 weeks (~4 months)

That’s realistic.

🧠 Where Solo Founders Get Stuck

Overbuilding reporting

Designing perfect UI

Trying to integrate accounting

Adding “nice-to-have” features

Refactoring too early

Stay focused on:

Ticket engine + vendor performance + storm workflow.

🚀 Faster Strategy (If You Want Revenue Sooner)

You could do a Lean V1:

Cut:

Pool logs

Advanced vendor metrics

Beautiful dashboards

Complex reporting

Build only:

Multi-tenant

Ticket engine

Vendor assignment

Basic dashboard

Storm tagging

That version:

~350 hours
= 4 months part-time
= 2.5 months full-time

Then onboard 2 pilot companies.

💰 Revenue Timing Reality

If you start now:

Month 1–2: validation + foundation

Month 3–5: core build

Month 6–7: pilots

Month 8–9: first paying customers

B2B sales cycle adds time.

🧩 Important Question

Are you planning:

A) Side project while employed
B) Full-time commitment
C) Build with one junior dev
D) Build and try to sell before MVP is done

Your timeline strategy changes depending on that answer.

Tell me which one you are, and I’ll optimize the execution plan accordingly.